## ActionItems
AI Customer Analyzer - DreamSpace
Week 1
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Choose organization | Responsible | Accountable | Informed | Consulted | Informed
| Identify organization needs | Accountable | Responsible | Informed | Consulted | Informed
| Contact organization and have an initial call with CEO | Accountable | Responsible | Informed | Informed | Consulted
| Requirement gathering process | Accountable | Responsible | Consulted | Consulted | Informed
| Get acceptance letter | Responsible | Accountable | Informed | Informed | Consulted
| Daily log | Accountable | Consulted | Informed | Informed | Responsible
| Prepare project brief document | Responsible | Accountable | Consulted | Consulted | Informed
| Draw use case diagram | Responsible | Accountable | Accountable | Consulted | Informed
| Meeting Minutes | Accountable | Consulted | Informed | Informed | Responsible
| Choose PM Tools | Responsible | Accountable | Informed | Consulted | Informed
| Setup PM tools | Responsible | Consulted | Consulted | Accountable | Informed
| Analyze collected requirements | Consulted | Responsible | Accountable | Informed | Informed
| Identify risk on collected requirements | Accountable | Informed | Responsible | Consulted | Informed
| Analyze requirements and set quality criteria | Accountable | Informed | Consulted | Responsible | Informed
Week 2
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Project proposal presentation | Responsible | Accountable | Informed | Consulted | Informed
| Daily log | Accountable | Informed | Informed | Consulted | Responsible
| Create architecture diagram | Responsible | Accountable | Informed | Consulted | Informed
| Meeting Minutes | Consulted | Accountable | Informed | Informed | Responsible
| Project proposal document | Responsible | Responsible | Consulted | Accountable | Informed
| Product description document | Accountable | Responsible | Informed | Consulted | Informed
| Create product flow diagram | Responsible | Accountable | Informed | Consulted | Informed
| Project plan document | Responsible | Responsible | Informed | Accountable | Informed
| Work breakdown structure | Responsible | Accountable | Informed | Consulted | Informed
| Project Board Meeting | Responsible | Accountable | Informed | Consulted | Informed
| Have a call with a client | Consulted | Responsible | Informed | Informed | Accountable
| Define the scope of projects | Responsible | Accountable | Informed | Informed | Consulted
| Define the objective of the project | Responsible | Accountable | Consulted | Informed | Informed
| Understand client expectations | Accountable | Responsible | Consulted | Consulted | Informed
Week 3
| ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Daily Log | Consulted | Accountable | Informed | Informed | Responsible
| Project quality plan document | Accountable | Consulted | Informed | Responsible | Informed
| Gant Chart | Accountable | Responsible | Informed | Consulted | Informed
| Project Board Meeting Minutes | Accountable | Informed | Informed | Consulted | Responsible
| Client Meeting Minutes | Informed | Accountable | Informed | Accountable | Responsible
| Risk Plan | Accountable | Informed | Responsible | Consulted | Informed
| Integrate PM tools with dev environment | Responsible | Informed | Informed | Accountable | Consulted
| Setup GitHub | Responsible | Accountable | Consulted | Informed | Informed
| Initialize the project | Accountable | Responsible | Informed | Consulted | Informed
| Discussed risk plan | Consulted | Informed | Responsible | Accountable | Informed
| Identify further risk in the requirement | Consulted | Informed | Responsible | Accountable | Informed
| Identify quality criteria | Consulted | Informed | Accountable | Responsible | Informed
| Identify further risk in the requirement | Consulted | Informed | Responsible | Accountable | Informed
| Do research on computer vision and build frame analyzer | Responsible | Accountable | Informed | Consulted | Informed
| Create repo structure & start initial coding works | Responsible | Accountable | Informed | Consulted | Informed
Week 4
| ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| SRS Document | Consulted | Responsible | Informed | Accountable | Informed
| Client Meeting Minutes | Informed | Consulted | Informed | Accountable | Responsible
| UI UX Design | Responsible | Accountable | Informed | Consulted | Informed
| Risk Plan | Accountable | Informed | Responsible | Consulted | Informed
| Business Case Document | Accountable | Responsible | Consulted | Informed | Informed
| Communication Plan | Accountable | Consulted | Informed | Informed | Responsible
| Project Initiation Document | Responsible | Accountable | Informed | Consulted | Informed
| Stage Plan | Responsible | Accountable | Consulted | Informed | Informed
| Setup GitHub | Responsible | Accountable | Informed | Consulted | Informed
| Connect GitHub with Azure Board | Responsible | Consulted | Informed | Accountable | Informed
| Build first prototype | Responsible | Accountable | Consulted | Informed | Informed
| Build code to access camera | Responsible | Consulted | Informed | Accountable | Informed
| Code clean up | Accountable | Consulted | Informed | Responsible | Informed
| Code review | Responsible | Accountable | Informed | Consulted | Informed
| Able to detect customer's face | Responsible | Consulted | Informed | Accountable | Informed
| Able to count | Responsible | Accountable | Informed | Consulted | Informed
| Test the first build to validate | Informed | Consulted | Accountable | Responsible | Informed
Week 5
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Product Breakdown Structure (PBS) | Responsible | Accountable | Informed | Consulted | Informed
| SBS Diagram | Responsible | Accountable | Informed | Consulted | Informed
| Networking diagrams | Responsible | Accountable | Informed | Consulted | Informed
| PDM diagram | Responsible | Responsible | Consulted | Responsible | Informed
| AON Diagram | Responsible | Accountable | Informed | Consulted | Informed
| Highlight Report | Responsible | Responsible | Responsible | Responsible | Responsible
| Quality Log | Consulted | Informed | Accountable | Responsible | Informed
| Acceptance Criteria Report | Consulted | Informed | Accountable | Responsible | Informed
| Build a face detection model | Responsible | Accountable | Informed | Responsible | Informed
| Setup window height and width | Accountable | Responsible | Informed | Consulted | Informed
| Write logic to access the camera | Responsible | Accountable | Informed | Consulted | Informed
| Write logic to preprocess vision | Responsible | Responsible | Informed | Accountable | Informed
| Build a face mask detection model | Responsible | Accountable | Informed | Consulted | Informed
| Write logic to count visitors | Responsible | Accountable | Informed | Consulted | Informed
| Write logic to get ROI region | Responsible | Consulted | Informed | Accountable | Informed
| Write logic to store detection information | Responsible | Accountable | Consulted | Informed | Informed
| Setup age detection model | Responsible | Informed | Informed | Accountable | Consulted
| Setup gender detection model | Responsible | Accountable | Informed | Informed | Consulted
| Setup emotion detection model | Responsible | Accountable | Informed | Consulted | Informed
| Setup race detection model | Responsible | Accountable | Consulted | Informed | Informed
| Configure dependencies & create as a conda env | Responsible | Consulted | Informed | Accountable | Informed
| Write logics to cluster races into aisgn, black and white | Responsible | Accountable | Informed | Consulted | Informed
| Write logics to save images with detection titles | Responsible | Consulted | Informed | Accountable | Informed
| Write logics to update database after saving detection images | Responsible | Accountable | Informed | Consulted | Informed
Week 6
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Highlight Report | Responsible | Responsible | Responsible | Responsible | Responsible
| ENV Report | Accountable | Responsible | Consulted | Informed | Informed
| Quality Log | Informed | Consulted | Responsible | Accountable | Informed
| Risk Register | Informed | Consulted | Responsible | Accountable | Informed
| Risk Profile | Informed | Consulted | Responsible | Accountable | Informed
| Lessons Learned Report | Responsible | Accountable | Informed | Informed | Consulted
| Project Board Meeting Minutes | Responsible | Accountable | Consulted | Informed | Informed
| Work Package | Responsible | Accountable | Informed | Consulted | Informed
| Code of Contact | Accountable | Responsible | Informed | Informed | Consulted
| Build base monitoring system template | Responsible | Consulted | Informed | Accountable | Informed
| Cleanup monitoring system template | Accountable | Consulted | Informed | Responsible | Informed
| Build pages in HTML / CSS | Accountable | Responsible | Responsible | Responsible | Responsible
| Implement positive-negative classification | Responsible | Accountable | Informed | Consulted | Informed
| Create a Home page in HTML / CSS | Responsible | Consulted | Informed | Accountable | Informed
| Create Vision data page in HTML / CSS | Responsible | Accountable | Informed | Consulted | Informed
| Create line charts/pie charts in JavaScript | Responsible | Accountable | Informed | Consulted | Informed
| Create audio data page in HTML / CSS | Responsible | Accountable | Consulted | Informed | Informed
| Create settings page in HTML / CSS | Responsible | Accountable | Informed | Consulted | Informed
| Code Review ¦ Code Cleanup | Accountable | Consulted | Informed | Responsible | Informed
| Model Testing | Accountable | Consulted | Informed | Responsible | Informed
Week 7
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Checkpoint Report | Responsible | Accountable | Informed | Consulted | Informed
| Off Specification Report | Accountable | Responsible | Consulted | Informed | Informed
| Business Case Updated Version | Informed | Responsible | Consulted | Accountable | Informed
| Code of Conduct | Responsible | Accountable | Informed | Informed | Consulted
| Highlight Report 2 | Responsible | Consulted | Informed | Informed | Accountable
| Lessons Learned Report | Responsible | Accountable | Informed | Informed | Consulted
| Project Approach | Responsible | Accountable | Informed | Informed | Consulted
| Work Package | Accountable | Responsible | Informed | Consulted | Informed
| Add versioning in config/app.php | Responsible | Informed | Informed | Accountable | Consulted
| Build home page in Laravel blade | Accountable | Consulted | Informed | Responsible | Informed
| Add change voice settings function | Responsible | Accountable | Informed | Consulted | Informed
| Create a AuthenticationController | Responsible | Consulted | Informed | Accountable | Informed
| Create a PageController | Responsible | Accountable | Informed | Informed | Consulted
| create a route for index | Responsible | Accountable | Informed | Accountable | Consulted
| build homepage.blade.php | Responsible | Accountable | Informed | Consulted | Informed
| Add password change function | Accountable | Accountable | Informed | Responsible | Informed
| Create CurdController | Responsible | Accountable | Consulted | Informed | Informed
| Build vision data searching by date | Accountable | Responsible | Informed | Informed | Consulted
| Build login page in Laravel blade | Accountable | Consulted | Informed | Informed | Responsible
| Build vision data page in Laravel blade | Accountable | Responsible | Informed | Informed | Consulted
| Build audio data page in Laravel blade | Accountable | Informed | Responsible | Consulted | Informed
| Build settings page in Laravel blade | Accountable | Informed | Consulted | Responsible | Informed
| Write route logics | Responsible | Informed | Consulted | Accountable | Informed
| Write form processing logics in controller | Responsible | Accountable | Consulted | Informed | Informed
| Write page controller logics | Responsible | Informed | Consulted | Accountable | Informed
Week 8
ACTION ITEM | ACTION ITEM | Project Manager | Startup Manager | Risk Manager | Quality Manager | Schedule Manager
| Product Checklist | Responsible | Accountable | Informed | Consulted | Informed
| Projec Issue | Consulted | Accountable | Responsible | Informed | Informed
| Post Project Review Plan | Accountable | Responsible | Consulted | Informed | Informed
| RACI Matrix Document | Responsible | Accountable | Informed | Informed | Consulted
| Daily log | Informed | Accountable | Consulted | Informed | Responsible
| Client Deployment Meeting | Responsible | Accountable | Informed | Informed | Informed
| Build UI to filter by month | Responsible | Accountable | Informed | Consulted | Informed
| Add search_by_month as a parameter | Responsible | Informed | Informed | Accountable | Consulted
| Get the current year & month | Responsible | Consulted | Informed | Responsible | Informed
| Plot the data from the database into the line chart customer | Responsible | Accountable | Informed | Consulted | Informed
| Plot data from database into race pie chart | Responsible | Consulted | Informed | Accountable | Informed
| Plot data from database into mask pie chart | Responsible | Accountable | Informed | Informed | Consulted
| Plot data from database into gender and age | Responsible | Consulted | Informed | Accountable | Informed
| Update Database | Responsible | Accountable | Consulted | Informed | Informed
| Implement FTP to transfer images to backend panel | Responsible | Accountable | Informed | Informed | Consulted

## Help
HELP |  | © 2017-2021 Vertex42.com
https://www.vertex42.com/ExcelTemplates/action-items-template.html
About
This template provides a simple way to track action items assigned to different members of a group. The template includes two different ways to show priority, using Low/Medium/High or a numeric Rank. You can use them both or delete the column you don't want to use.
Create and track your project schedule easily using the Excel Gantt Chart Template by Vertex42.com.
Learn More
More To Do List Templates
To learn how to add drop-down lists and use conditional formatting to spice up your task lists, see the article listed below.
Add Cool Features to Your To Do Lists
Editing the Drop-Down Lists
To edit the drop-down list in the Priority column, select the cells you want to edit then go to Data > Data Validation.
If you change the list of items in the Priority drop-down list, then you may need to edit the conditional formatting rule(s) as well.
Conditional Formatting
To edit conditional formatting rules, go to Conditional Formatting > Manage Rules and select "This Worksheet" to see and edit all the rules.
When you mark the Done column with a check, a conditional formatting rule will change the font in that row to gray.
Terms of Use
This spreadsheet, including all worksheets and associated content is a copyrighted work under the United States and other copyright laws.
Do not submit copies or modifications of this template to any website or online template gallery. Please review the following license agreement to learn how you may or may not use this template. Thank you.
https://www.vertex42.com/licensing/EULA_privateuse.html